## project
Project: | Web Development and User Authentication System
Developer: | ZIROH K. MAE
Starting Date: | 2023-11-12
Ending Date: | 2023-12-25
Milestone description | Assigned to | Progress | Start | End | Duration
INSTALLATION & CONFIGARATION |  |  |  |  | 0
Downloading Xampp | Ziroh | 1% | 2023-11-12 | 2023-12-12 | 0.1
Installation |  | 1% | 2023-11-13 | 2023-12-13 | 0.3
Msql Configuration |  | 1% | 2023-11-14 | 2023-12-14 | 0.3
Apache Configuration |  | 1% | 2023-11-15 | 2023-12-15 | 0.2
lunching the Localhost |  | 1% | 2023-11-16 | 2023-12-16 | 0.1
Database
Create Signup_Login Database | Ziroh | 3% | 13/12/2023 | 14/12/2023 | 0.2
create table User under signup_login |  | 3% | 13/12/2024 | 14/12/2024 | 0.5
Open Localhost |  | 3% | 13/12/2025 | 14/12/2025 | 0.3
Coding
index.php page |  | 15% | 15/12/2023 | 16/12/2023 | 0.25
Signup.html page |  | 16% | 16/12/2023 | 17/12/2023 | 0.25
database.php page |  | 5% | 17/12/2023 | 18/12/2023 | 0.1
Login.Php page |  | 16% | 18/12/2023 | 19/12/2023 | 0.1
Process-SignupPhp page |  | 8% | 19/12/2023 | 20/12/2023 | 0.2
Logout.Php page |  | 8% | 20/12/1023 | 21/12/2023 | 0.1
Validation
Email Validation |  | 2% | 21/12/2023 | 22/12/2023 | 0.6
signup-succesful.html |  | 2% | 22/12/2023 | 23/12/2023 | 0.4
Styling
Style.css |  | 12% | 23/12/2023 | 25/12/2023 | 2
Run Bedbeging |  | 1% | 25/12/2023 | 25/12/2023 | 1
Test |  | 1% | ok | ok